COFFEE SHOP BASECAMP 30-Day Pre-Opening Marketing Calendar Week 7 Operational Template — Coffee Shop Basecamp

| SHOP NAME | PLANNED OPENING DATE | DAY 1 OF PRE-OPENING (30 DAYS BEFORE) |
| --- | --- | --- |

| Week 1 — Lay the Foundation Days 1–7 · Set up, claim, and tell people who already know you |  |  |
| --- | --- | --- |
| Day | Focus | Your Actions |
| Days 1–2 | Digital Setup Claim or refresh Google Business Profile. Set up or update Instagram. Link your social bio to an email sign-up. Make sure all profile details are complete. | Notes / Actions |
| Days 3–4 | Personal Network Tell people who already know you — friends, family, former colleagues. A direct message beats a broadcast post every time. | Notes / Actions |
| Days 5–7 | First Community Contacts Visit two of your five community partners in person. Introduce yourself. Leave a flyer or card. First contact only — no ask required. | Notes / Actions |
| Checkpoint: By end of Day 7: digital presence live, personal network informed, two community introductions made. |  |  |

| Week 2 — Tell Your Story Days 8–14 · Go public and pitch local press |  |  |
| --- | --- | --- |
| Day | Focus | Your Actions |
| Days 8–9 | Opening Story Post Post your opening announcement on Instagram. Use your Format B caption. Make it feel like a real person talking, not a launch announcement. | Notes / Actions |
| Days 10–11 | Press Outreach Send your press pitch to local food journalists, neighbourhood blogs, and community newsletters. Give them 2-3 weeks lead time from now. | Notes / Actions |
| Days 12–14 | Behind-the-Scenes Content Post 2-3 times: fit-out progress, your first espresso pull, a team introduction, or your bar taking shape. Show the process. | Notes / Actions |
| Checkpoint: By end of Day 14: opening story public, press pitched, three community relationships made. |  |  |

| Week 3 — Build Anticipation Days 15–21 · Soft opening, feedback, and final outreach |  |  |
| --- | --- | --- |
| Day | Focus | Your Actions |
| Days 15–17 | Soft Opening (if running one) Invite-only event for 20-40 people. Family, friends, neighbouring businesses, local press. Be clear: this is practice, feedback is welcome, service will be slower than normal. | Notes / Actions |
| Days 18–19 | Final Community Contacts Complete your five community relationships. Follow up with anyone who expressed interest. Confirm specific arrangements. | Notes / Actions |
| Days 20–21 | Opening Date Announcement Post your confirmed opening date publicly. Not a vague 'coming soon' — a specific date. Give people something to put in their diary. | Notes / Actions |
| Checkpoint: By end of Day 21: soft opening complete, all five relationships made, opening date public. |  |  |

| Week 4 — Open Strong Days 22–30 · Team brief, countdown, and opening day |  |  |
| --- | --- | --- |
| Day | Focus | Your Actions |
| Days 22–25 | Team Opening Brief Brief your team on the opening day plan. Culture first, then tasks. Over-staff it. Decide in advance how to handle a longer queue — and brief the team on how to communicate it warmly. | Notes / Actions |
| Days 26–28 | Final Countdown Content Post 2-3 times in the final week. Build excitement without overselling. Show the team, the space, the product. Remind people of the date and the address. | Notes / Actions |
| Day 30 | Opening Day Be on the floor. Meet people. Collect contact details from every person who comes in. Ask for honest feedback directly. Run a debrief with the team after service. | Notes / Actions |
| Checkpoint: Open on the date you announced, with a team who knows the plan, and a way to capture the details of every person who walks in. |  |  |

Timberline Coffee School  |  Coffee Shop Basecamp  |  Week 7  |  30-Day Marketing Calendar